## Your Rev Projection
Revenue Forecast |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
12-month Rolling Revenue Projection |  |  |  |  | 3: Required Annual Revenue; 6: 7000000
| Projected Revenue = the actual value of the work performed including: Direct Costs + Indirect Costs + Proft |  |  |  | 4: Months; 6: 12
| Revenue Projections are NOT representative of front-loading or overbilling. Revenue is the real value of the work perfomed. |  |  |  | 4: Req. Rev. Month; 6: 583333.3333
Example: | Business Plan for Division = $7,000,000 Annual Gross Revenue @ 20% Gross Margin (25% Gross Mark-up)
| Net Revenue Required Per Month to Have a Viable Operation |  |  |  | 1: 583333.3333
Must sell and install this much good work, that will produce revenues in the appropriate months to ensure division viability!
Step #1: | Project your anticipated revenue over the duration of the job. This must be schedule-driven.
Do this for three different sets of jobs in your firm:
1. Open contracts - Jobs already in progress - project the balance of the revenue to be earned.
2. Booked jobs not yet started - project the expected revenue to be earned over the course of the job.
3. Bid jobs, not yet awarded, that you believe have a high probability of being awarded.
Division: | Commercial |  |  |  | 1: Pre-COVID-19: Projected Revenue Forecast - 12-month Rolling Forecast
Open Contracts |  | Contract Amt | Gross Revenue | Gross Revenue | 1: Current Mo. | Amount of Revenue Remaining to Be Earned | Months of Revenue Remaining
Job # | Job Name | + Approved COs | Earned to Date | Remaining | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01
CEN002 | Centre St Professional | 11700 | 9315 | 2385 | 2385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CEN003 | Centre Sq. Retail | 10152 | 1500 | 8652 | 6000 | 2652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HIN002 | Hinman Trade Center | 62142 | 19611 | 42531 | 15000 | 15000 | 12531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOU002 | South Haven Public School | 1131167 | 233000 | 898167 | 155000 | 279000 | 303000 | 140000 | 21167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STR005 | Stryker Medical | 3207009 | 515000 | 2692009 | 333000 | 360000 | 409000 | 400000 | 320000 | 315000 | 298000 | 250000 | 7009 | 0 | 0 | 0 | 0
M43002 | M43 Retail C | 13426 | 2000 | 11426 | 2000 | 3000 | 6426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MEI001 | Meijer Store 119 | 111734 | 1500 | 110234 | 10000 | 33000 | 50000 | 17234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Open Jobs | 4547330 | 781926 | 3765404 | 523385 | 692652 | 780957 | 557234 | 341167 | 315000 | 298000 | 250000 | 7009 | 0 | 0 | 0 | 0
Booked Jobs - Not Started
FAM002 | Family Health | 233558 | 0 | 233558 | 0 | 0 | 0 | 10000 | 30000 | 50000 | 95000 | 35000 | 13558 | 0 | 0 | 0 | 0
FUL001 | Full City Café | 55800 | 0 | 55800 | 0 | 0 | 0 | 0 | 20000 | 18000 | 17800 | 0 | 0 | 0 | 0 | 0 | 0
PAP001 | Papa Murphy's | 100800 | 0 | 100800 | 0 | 0 | 0 | 0 | 0 | 15000 | 20000 | 30000 | 23000 | 12800 | 0 | 0 | 0
0
| Total Booked Jobs | 390158 | 0 | 390158 | 0 | 0 | 0 | 10000 | 50000 | 83000 | 132800 | 65000 | 36558 | 12800 | 0 | 0 | 0
Proposed Projects - High Probability of Getting (80% sure) Use 70% of Revenue
| Richland Bible Church | 980000 | 0 | 686000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 75000 | 100000 | 100000 | 100000 | 100000 | 161000 | 3
| Great Amercian Tower | 3933385 | 0 | 2753369.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61000 | 119000 | 250000 | 250000 | 300000 | 1773369.5 | 12
| Ritz Carlton - La Jolla | 154793 | 0 | 108355.1 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 25000 | 10000 | 10000 | 3355 | 0 | 0.1 | 0
| Ximed Medical Office Bulding | 1182814 | 0 | 827969.8 | 0 | 0 | 0 | 0 | 0 | 0 | 64000 | 50000 | 98000 | 100000 | 90000 | 90000 | 335969.8 | 5
| Four Seasons Hotel - Aviara | 5310000 | 0 | 3717000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 66000 | 150000 | 3486000 | 14
| Kaiser Permanente Eastlake | 152473 | 0 | 106731.1 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 16731 | 0 | 0 | 0 | 0.1
| Pac Center - NBC | 57743 | 0 | 40420.1 | 0 | 0 | 15000 | 18000 | 1500 | 5920 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1
| Total Proposed Jobs | 11771208 | 0 | 8239845.6 | 0 | 0 | 15000 | 18000 | 1500 | 65920 | 174000 | 241000 | 343731 | 475000 | 509355 | 640000 | 5756339.6
| Total | 16708696 | 781926 | 12395407.6 | 523385 | 692652 | 795957 | 585234 | 392667 | 463920 | 604800 | 556000 | 387298 | 487800 | 509355 | 640000 | 5756339.6
|  |  |  | Monthly Required Revenue: Over/Under | -59948.3333 | 109318.6667 | 212623.6667 | 1900.6667 | -190666.3333 | -119413.3333 | 21466.6667 | -27333.3333 | -196035.3333 | -95533.3333 | -73978.3333 | 56666.6667
For informational purposes only, use at your own risk.
0
0
0
0

## Your Immediate COVID-19 Changes
Revenue Forecast |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
12-month Rolling Revenue Projection |  |  |  |  | 3: Required Annual Revenue; 6: 7000000
| Projected Revenue = the actual value of the work performed including: Direct Costs + Indirect Costs + Proft |  |  |  | 4: Months; 6: 12
| Revenue Projections are NOT representative of front-loading or overbilling. Revenue is the real value of the work perfomed. |  |  |  | 4: Req. Rev. Month; 6: 583333.3333
Example: | Business Plan for Division = $7,000,000 Annual Gross Revenue @ 20% Gross Margin (25% Gross Mark-up)
| Net Revenue Required Per Month to Have a Viable Operation |  |  |  | 1: 583333.3333
Must sell and install this much good work, that will produce revenues in the appropriate months to ensure division viability!
Step #2: | Project your changes to projected revenue based on COVID-19 & Economy 2020/2021 fall-out.
Most Common Changes:
1. Open contracts - Delays caused by project shutdown or slowdown. Acceleration caused by opportuntistic customers, e.g. School Corps.
2. Booked jobs not yet started - Projects delayed or put on hold. Projects accelerated.
3. Bid jobs, not yet awarded, that you believe have a high probability of being awarded. - Projects delayed or cancelled.
Division: | Commercial |  |  |  | 1: Pre-COVID-19: Projected Revenue Forecast - 12-month Rolling Forecast
Open Contracts |  | Contract Amt | Gross Revenue | Gross Revenue | 1: Current Mo. | Amount of Revenue Remaining to Be Earned | Months of Revenue Remaining
Job # | Job Name | + Approved COs | Earned to Date | Remaining | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01
CEN002 | Centre St Professional | 11700 | 9315 | 2385 | 0 | 0 | 0 | 2385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CEN003 | Centre Sq. Retail | 10152 | 1500 | 8652 | 0 | 0 | 6000 | 2652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HIN002 | Hinman Trade Center | 62142 | 19611 | 42531 | 0 | 0 | 15000 | 15000 | 12531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOU002 | South Haven Public School | 1131167 | 233000 | 898167 | 300000 | 300000 | 250000 | 48167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STR005 | Stryker Medical | 3207009 | 515000 | 2692009 | 333000 | 360000 | 409000 | 400000 | 320000 | 315000 | 298000 | 250000 | 7009 | 0 | 0 | 0 | 0
M43002 | M43 Retail C | 13426 | 2000 | 11426 | 0 | 0 | 2000 | 3000 | 6426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MEI001 | Meijer Store 119 | 111734 | 1500 | 110234 | 0 | 0 | 0 | 10000 | 33000 | 50000 | 17234 | 0 | 0 | 0 | 0 | 0 | 0
| Total Open Jobs | 4547330 | 781926 | 3765404 | 633000 | 660000 | 682000 | 481204 | 371957 | 365000 | 315234 | 250000 | 7009 | 0 | 0 | 0 | 0
Booked Jobs - Not Started
FAM002 | Family Health | 233558 | 0 | 233558 | 0 | 0 | 0 | 10000 | 30000 | 50000 | 95000 | 35000 | 13558 | 0 | 0 | 0 | 0
FUL001 | Full City Café | 55800 | 0 | 55800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55800
PAP001 | Papa Murphy's | 100800 | 0 | 100800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 20000 | 30000 | 23000 | 12800 | 0
| Total Booked Jobs | 390158 | 0 | 390158 | 0 | 0 | 0 | 10000 | 30000 | 50000 | 95000 | 50000 | 33558 | 30000 | 23000 | 12800 | 55800
0
Proposed Projects - High Probability of Getting (80% sure) Use 70% of Revenue | [16 empty] | 0
| Richland Bible Church | 980000 | 0 | 686000 | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2021-04-01: 50000 | 636000 | 3
| Great Amercian Tower | 3933385 | 0 | 2753369.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61000 | 119000 | 250000 | 2323369.5 | 12
| Ritz Carlton - La Jolla | 154793 | 0 | 108355.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 30000 | 10000 | 18355 | 0 | 0.1 | 0
| Ximed Medical Office Bulding | 1182814 | 0 | 827969.8 | 0 | 0 | 0 | 0 | 64000 | 50000 | 98000 | 100000 | 90000 | 90000 | 150000 | 150000 | 35969.8 | 5
| Four Seasons Hotel - Aviara | 5310000 | 0 | 3717000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 66000 | 150000 | 3486000 | 14
| Kaiser Permanente Eastlake | 152473 | 0 | 106731.1 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 16731 | 0 | 0 | 0 | 0.1
| Pac Center - NBC | 57743 | 0 | 40420.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40420.1
| Total Proposed Jobs | 11771208 | 0 | 8239845.6 | 0 | 0 | 0 | 0 | 64000 | 80000 | 128000 | 180000 | 136731 | 176000 | 353355 | 600000 | 6521759.6
0
| Total | 16708696 | 781926 | 12395407.6 | 633000 | 660000 | 682000 | 491204 | 465957 | 495000 | 538234 | 480000 | 177298 | 206000 | 376355 | 612800 | 6577559.6
|  |  |  | Monthly Required Revenue: Over/Under | 49666.6667 | 76666.6667 | 98666.6667 | -92129.3333 | -117376.3333 | -88333.3333 | -45099.3333 | -103333.3333 | -406035.3333 | -377333.3333 | -206978.3333 | 29466.6667
Earned Revenue
Step #3: | Identify any projected revenue shortfalls or overages. |  |  |  | 2020-09-01: Direct Cost; 2020-10-01: 80000; 2020-12-01: 65000
[9 empty] | Indirect Cost | 12% | 9600 | 7800
| 1. Determine if a modification in field workforce, office staff, or management is required and adjust accordingly. |  |  |  | 2020-09-01: Total; 2020-11-01: 89600; 2020-12-01: 72800
| 2. Identify marketing and sales opportuntites specifically chosen to respond to your revenue projection. |  |  |  | 2020-09-01: Profit; 2020-10-01: 20%; 2020-11-01: 17920; 2020-12-01: 29120; 2021-01-01: 40%
| 3. Closely examine your projected cash flows (remember you typically have a 60-day lag). Identify required cash and determine strategy to achieve it. |  |  |  | 2020-10-01: ER; 2020-11-01: 107520; 2020-12-01: 101920
0
0
0
0